## Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
• Read cell comments in the table header row for more information
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2020-11-02 | 2020-11-02 | 1 | Proposal Accepted | -10 | -10
2020-11-03 | 2020-11-04 | 2 | Team Schedule | -17 | -17
2020-11-05 | 2020-11-11 | 7 | Content Research | -24 | -24
2020-11-12 | 2020-11-14 | 3 | Content Draft and Edit | -31 | -31
2020-11-15 | 2020-11-16 | 2 | Content Approval | -38 | -38
2020-11-17 | 2020-11-23 | 7 | Multimedia production | -45 | -45
2020-11-24 | 2020-11-30 | 7 | Multimedia Edits | -52 | -52
2020-12-01 | 2020-12-05 | 5 | Content Compile | -59 | -59
2020-12-06 | 2020-12-07 | 2 | Content Upload | -66 | -66
2020-12-08 | 2020-12-14 | 7 | Section Test | -73 | -73
2020-12-15 | 2020-12-21 | 7 | Initial Review | -66 | -66
2020-12-22 | 2020-12-28 | 7 | Review Based Edits | -59 | -59
2020-12-29 | 2021-01-04 | 7 | 2nd Review | -52 | -52
2021-01-05 | 2021-01-09 | 5 | Final Review Edit | -45 | -45
2021-01-10 | 2021-01-15 | 6 | Live Test | -38 | -38
2021-01-16 | 2021-01-18 | 3 | Project Finalization | -31 | -31
2021-01-19 | 2021-01-19 | 1 | Project Completion Approved | -24 | -24
Insert new rows above this one
Milestones | Project Start Date | 2020-11-02
Date |  |  | Label | Position
2020-11-02 |  |  | Kick Off! | 10
2020-11-09 |  |  | #1 - Schedule Check Adjust if Needed | 15
2020-11-16 |  |  | #2 - Content Complete | 20
2020-11-23 |  |  | #3 - Multimedia Production Complete | 25
2020-11-30 |  |  | #4 - Multimedia Final Edit | 30
2020-12-07 |  |  | #5 - Content Upload Complete | 35
2020-12-14 |  |  | #6 - Half Way - Check in Confirm on Track | 40
2020-12-21 |  |  | #7 - First Review Complete | 35
2020-12-28 |  |  | #8 - Review Edits Complete | 30
2021-01-04 |  |  | #9 - 2nd Review Complete | 25
2021-01-11 |  |  | #10 - Live Testing Begun | 15
2021-01-18 |  |  | #11- Project Finalization Complete | 10
2021-01-25 |  |  | #12- Project Complete | 5
Insert new rows above this one
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1
Start = [Start, row above]+7

## About (hidden)
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.